## Sheet1
Test ID | Test Type | User Story | Test Case Name | Test Steps | Expected Result | Actual Result | Test Status | Comments
US-01-1 | User Story | 1. As an applicant, I want to authenticate using my Google account, so that I am identified on my enrolment application. Authentication must use OpenID Connect. | Successful login - Applicant authentication | Launch app (http://www.optimizeprime.live), enter valid Google credentials | Access to app is granted, main applicant screen is displayed | PASS | COMPLETE - Aug 30 @ 2:02PM
US-01-2 | User Story | 1. As an applicant, I want to authenticate using my Google account, so that I am identified on my enrolment application. Authentication must use OpenID Connect. | Failed login - Applicant authentication | Launch app (http://www.optimizeprime.live), enter invalid Google credentials | Access to app is denied, appropriate error is displayed to user | PASS - Google authentication popup prevents moving forward | COMPLETE - Aug 30 @ 2:02PM
US-01-3 | User Story | 1. As an applicant, I want to authenticate using my Google account, so that I am identified on my enrolment application. Authentication must use OpenID Connect. | Logout of app | Launch app (http://www.optimizeprime.live), enter valid applicant credentials, log out of the app | User is successfully logged out and cannot enter app again without authenticating again | FAIL - After clicking Logout, I can navigate to and it does not reauthenticate http://www.optimizeprime.live/dashboard | COMPLETE - Aug 30 @ 2:02PM
US-01-4 | User Story | 1. As an applicant, I want to authenticate using my Google account, so that I am identified on my enrolment application. Authentication must use OpenID Connect. | Access admin screen as applicant | Launch app (http://www.optimizeprime.live), enter valid applicant credentials, attempt to access admin screen (via admin URL) | User cannot access admin screens (NOTE: There is no authentication for admin access) | N/A | NOT APPLICABLE - There is no requirement for authentication for admin screens
US-02-1 | User Story | 2. As an applicant, I may want to provide my 4-digit pharmacist registration number, so that I can prove my credentials. | Submit application - with reg number | Login as applicant, create application with 4-digit pharmacist reg number, submit for approval | Application is submitted, message is displayed to user that the application is submitted for approval (and will be automatically approved?) |  | No run
US-02-2 | User Story | 2. As an applicant, I may want to provide my 4-digit pharmacist registration number, so that I can prove my credentials. | Submit application - without reg number (NULL value) | Login as applicant, create application WITHOUT a pharmacist reg number (NULL value), submit for approval | Application is submitted, message is displayed to user that the application is submitted for approval (and will be need to be approved by admin) |  | No run
US-02-3 | User Story | 2. As an applicant, I may want to provide my 4-digit pharmacist registration number, so that I can prove my credentials. | Submit application - with invalid reg number (alpha value) | Login as applicant, create application with a non-numeric pharmacist reg number (alpha value), submit for approval | Error is displayed informing user the pharmacist reg number must be 4 digit and numeric |  | No run
US-02-4 | User Story | 2. As an applicant, I may want to provide my 4-digit pharmacist registration number, so that I can prove my credentials. | Submit application - with too short reg number | Login as applicant, create application with a 3 digit pharmacist reg number, submit for approval | Error is displayed informing user the pharmacist reg number must be 4 digit and numeric |  | No run
US-02-5 | User Story | 2. As an applicant, I may want to provide my 4-digit pharmacist registration number, so that I can prove my credentials. | Submit application - with too long reg number | Login as applicant, create application with a 5 digit pharmacist reg number, submit for approval | Error is displayed informing user the pharmacist reg number must be 4 digit and numeric |  | No run
US-03-1 | User Story | 3. As an applicant, I want to submit my application for enrolment, so that it can be processed. | Submit application - successful entry | Login as applicant, create application, enter details, submit for approval | Application is submitted, message is displayed to user that the application is submitted for approval |  | No run
US-03-2 | User Story | 3. As an applicant, I want to submit my application for enrolment, so that it can be processed. | Submit application - unsuccessful entry | Login as applicant, create application, enter incorrect details, submit for approval | Error is displayed informing user of incorrect details, cannot submit application |  | No run
US-03-3 | User Story | 3. As an applicant, I want to submit my application for enrolment, so that it can be processed. | Submit application - cancel entry | Login as applicant, create application, cancel application creation | Application is canceled, user is returned to main applicant screen |  | No run
US-04-1 | User Story | 4. As an administrator, I want all applications with a registration number to be automatically approved, so that I don't waste my time reviewing them. | Successful login - Admin authentication | Launch admin app, enter valid admin credentials | Access to app is granted, main admin screen is displayed (NOTE: Currently admin does not require credentials) |  | No run
US-04-2 | User Story | 4. As an administrator, I want all applications with a registration number to be automatically approved, so that I don't waste my time reviewing them. | Automatic approvals - with reg number | Login as applicant, create application with a pharmacist reg number, submit for enrolment, login as admin, open recently submitted application | Status of application is "Approved" |  | No run
US-04-3 | User Story | 4. As an administrator, I want all applications with a registration number to be automatically approved, so that I don't waste my time reviewing them. | Automatic approvals - without reg number (NULL value) | Login as applicant, create application WITHOUT a pharmacist reg number (null value), submit for enrolment, login as admin, open recently submitted application | Status of application is "Not Approved" |  | No run
US-05-1 | User Story | 5. As an administrator, I want to access an administrator interface using a separate URL, so that I can review applications. (The administrator does not need to be authenticated.) | Admin access | Launch admin app (http://www.optimizeprime.live/dashboard/admin) | Separate URL is used to access admin screens, admin screens are displayed, applications can be accessed from the admin view |  | No run
US-06-1 | User Story | 6. As an administrator, I want to see a list of all applications, so that I can review applications. | List applications | Launch admin app (http://www.optimizeprime.live/dashboard/admin), navigate to view of all applications | All applications are shown, regardless of status |  | No run
US-07-1 | User Story | 7. As an administrator, I want to see if an application has been approved, so that I can choose to review it if not. | View approved applications | Launch admin app (http://www.optimizeprime.live/dashboard/admin), navigate to view of all applications, filter list of applications based on status "Approved" | List of only "Approved" applications is displayed |  | No run
US-07-2 | User Story | 7. As an administrator, I want to see if an application has been approved, so that I can choose to review it if not. | View not approved applications | Launch admin app (http://www.optimizeprime.live/dashboard/admin), navigate to view of all applications, filter list of applications based on status "Not Approved" | List of only "Not Approved" applications is displayed |  | No run
US-07-4 | User Story | 7. As an administrator, I want to see if an application has been approved, so that I can choose to review it if not. | Review a not approved application | Launch admin app (http://www.optimizeprime.live/dashboard/admin), navigate to view of all applications, select an application with status "Not Approved", click "Review" | Application details are displayed |  | No run
NF-01 | Non-functional | N/A | 1. Solutions must be developed using technology and architectural style that demonstrates modern best practices. | Verify against architecture document and code reporitory | Architecture document and application code demostrates modern best practices |  | No run
NF-02 | Non-functional | N/A | 2. The solution must not include proprietary components. | Verify against architectural document and code repository | No proprietary components are included in architecture document or code repository |  | No run
NF-03 | Non-functional | N/A | 3. Solutions must be deployed to a Docker container platform | Run deployment steps, ensure that application is running within Docker containers | Application is running in Docker containers |  | No run
NF-04 | Non-functional | N/A | 4. The solution must remain running and accessible from 8:30 a.m. till 5:00 p.m. Pacific Time on Tuesday, September 3 | Deploy and ensure stability during timeframe | Solution remains available for timeframe |  | No run
NF-05 | Non-functional | N/A | 5. Dockerfiles must be committed to the private repository. | Verify the repository is private, attempt to access publicly | Repository cannot be accessed publicly, can be accessed privately |  | No run
NF-06 | Non-functional | N/A | 6. Solution must be re-deployable using an automated deployment tool | Solution uses GitLab CI. Verify that automated deployment works on GitLab CI | Automated deployment is successful |  | No run
NF-07 | Non-functional | N/A | 7. Configuration files for that tool must be committed to the private repository | Ensure deployment config files are deployed to the repository | Config files are accessible in repo |  | No run
NF-08 | Non-functional | N/A | Attach an Apache License 2.0 to the Deliverable. | Ensure Apache licence is deployed to the repository | Apache licence is included |  | No run